## Safari To Do
Safari Adventure Camp 2026 — Planning To Do
Example planning timeline for an overnight Meerkat camp (ages 5–6)
Editable example for Den Scouters — adapt names, dates, venue details, quantities, and leadership assignments to your own camp.
Overnight non-negotiables: at least one parent camps with each Meerkat; no electronics for children; no alcohol; Meerkats arrive in full uniform with hat and scarf.
Done | Timing | Safari Planning Task | Why It Matters / Practical Note
2 Months Ahead — Map the Safari
☐ | 2 months ahead | Appoint the Camp Leader, safety lead, food lead, activity lead, and one Burrow Leader per group. | Create a clear communication channel for adult volunteers and record their roles.
☐ | 2 months ahead | Confirm the campsite, overnight arrangements, ablutions, water points, cooking areas, and emergency access. | Visit the site if possible and identify the Lion’s Den, Elephant’s Trail, Hippo’s Oasis, craft area, kitchen, campfire, and quiet zone.
☐ | 2 months ahead | Draft the Safari Camp Program, risk assessment, first-aid plan, and weather back-up plan. | Use the example program in the second tab as a starting point; keep activities short and age-appropriate for 5–6-year-olds.
☐ | 2 months ahead | Send the first parent communication and RSVP form. | State clearly that at least one parent must camp with each Meerkat and that children may not bring electronics.
4 Weeks Ahead — Assemble the Safari Team
☐ | 4 weeks ahead | Send the detailed camp letter with cost, consent form, medical and dietary information request, kit list, and programme outline. | Include arrival in full uniform with hat and scarf; explain that the camp is alcohol-free.
☐ | 4 weeks ahead | Apply for the camp permit or secure the approval required by your Group, District, and venue. | Attach the camp programme and relevant safety information.
☐ | 4 weeks ahead | Allocate families and Scouters to Burrows and begin assigning food, equipment, activity, and clean-up responsibilities. | Keep siblings together where possible and ensure each Burrow has sufficient adult support.
☐ | 4 weeks ahead | Check badge opportunities against the programme: Little Camper, Cooking, Eco-Warrior, and Bug Hunter. | Choose only tasks that can be completed safely and naturally during camp.
3 Weeks Ahead — Prepare the Safari Base
☐ | 3 weeks ahead | Confirm attendance, consent forms, medication, allergies, dietary requirements, emergency contacts, and parent camping arrangements. | Follow up promptly on missing information; do not assume an adult companion is attending.
☐ | 3 weeks ahead | Complete the venue-specific risk assessment for fire, water, roads, night activities, weather, food hygiene, and boundaries. | Plan a visible buddy system, whistle signal, adult supervision points, and an emergency assembly area.
☐ | 3 weeks ahead | Check shared equipment: first-aid kit, drinking-water containers, gazebos, tables, fire equipment, ropes, buckets, craft boxes, torches for adults, and signage. | Create a collection plan for anything borrowed from families or the Group.
☐ | 3 weeks ahead | Prepare activity resources and adult instructions for each Safari zone. | Pre-cut craft materials; for the bleach-print shirt option, all chemical handling is adult-only and needs its own risk controls.
2 Weeks Ahead — Confirm the Safari Route
☐ | 2 weeks ahead | Close the RSVP list and confirm the final numbers for Meerkats, parents, siblings, and Scouters. | Recalculate food, water, transport, sleeping-space, and activity quantities.
☐ | 2 weeks ahead | Collect outstanding forms and payments; record medication handover arrangements. | Keep a secure hard-copy attendance and emergency-contact pack at camp.
☐ | 2 weeks ahead | Confirm the menu, shopping responsibilities, food storage, Halaal or other dietary arrangements, and meal-serving equipment. | The menu is flexible: select meals suitable for your venue and cooking facilities.
☐ | 2 weeks ahead | Brief all adult volunteers on the programme, their Burrow role, safeguarding expectations, emergency plan, and camp rules. | Make sure adults know who is responsible for set-up, activities, meals, fires, clean-up, and overnight checks.
1 Week Ahead — Pack the Ranger Boxes
☐ | 1 week ahead | Buy non-perishable food and consumables; label boxes by meal or activity zone. | Separate food, craft, games, hygiene, and first-aid supplies so set-up is quicker.
☐ | 1 week ahead | Print the camp programme, attendance list, emergency contacts, consent/medical summary, menu, kit lists, badge trackers, and signage. | Keep digital copies with the Camp Leader, but do not rely on children having electronics.
☐ | 1 week ahead | Prepare the printable Safari stencil pack, animal-track cards, craft packs, game equipment, and award items. | Count everything against the final attendance list.
☐ | 1 week ahead | Send the final parent reminder. | Restate arrival time, full uniform, camping parent requirement, kit list, no alcohol, and no electronics for children.
2 Days Ahead — Final Safari Check
☐ | 2 days ahead | Confirm final attendance with every family and adult volunteer. | Update the emergency-contact pack and food numbers immediately if anything changes.
☐ | 2 days ahead | Check weather, route, campsite access, fire restrictions, and venue contact availability. | Activate the weather back-up programme if needed.
☐ | 2 days ahead | Pack shared camp equipment and activity boxes by zone. | Use a vehicle-loading checklist so nothing essential is left behind.
1 Day Before — Set the Safari Camp in Motion
☐ | 1 day before | Purchase perishables, chill food safely, and pack cooking, serving, and washing-up supplies. | Keep cold-chain foods separate and plan for safe storage at camp.
☐ | 1 day before | Pack the Camp Leader folder, first-aid supplies, safety gear, programme, and site maps. | Include incident-report forms and emergency numbers.
☐ | 1 day before | Do a final readiness call with the leadership team. | Confirm who arrives early to prepare registration, water, activity zones, and the adult briefing.

## Safari Camp Program
Safari Adventure Camp 2026 — Example Camp Program
Example overnight programme for Meerkats (ages 5–6), their camping parents, and Den Scouters
Editable example for Den Scouters — adapt names, dates, venue details, quantities, and leadership assignments to your own camp.
Use this as a flexible example. Keep one parent with every Meerkat overnight, make adult supervision visible, offer water often, and adjust activities for weather, venue rules, group size, and energy levels.
Time | Duration | Safari Activity | Lead & Support | Equipment / Set-up | Den Scouter Detail & Badge Link
DAY 1 — Arrival, Safari Adventure & Overnight Camp
10:00 | 30 min | Arrival & Ranger Registration | Camp Leader + registration team | Attendance sheet, consent/medical folder, pens, wrist/burrow markers | Welcome each family, check medication and final details, and record attendance. Remind families: adults stay with their Meerkats; no children’s electronics; no alcohol.
10:30 | 15 min | Opening Circle & Safari Rules | Camp Leader + all Burrow Leaders | Promise and Law, whistle, camp map | Introduce the whistle signal, buddy system, water points, boundaries, toilets, fire rules, wildlife respect, and the day’s Safari mission.
10:45 | 45 min | Set Up the Safari Base Camp | Burrow Leaders + camping parents | Tent areas, site map, name markers | Families set up together in Burrows. Meerkats help with simple jobs such as laying ground sheets, carrying soft gear, and identifying their sleeping space. Little Camper: Help pack / Sleep under the stars.
11:30 | 30 min | Lion’s Den: Ranger Rescue Relay | Games lead + Burrow Leaders | Soft toy animals, buckets, cones, whistle | Use a short, non-elimination relay. One Meerkat at a time rescues an animal and returns it to the Ranger Station. Offer a walking version if needed.
12:05 | 45 min | Crafty Chameleon: Safari Ranger T-Shirts | Craft lead + adult helpers | Dark cotton shirts, fabric paint, Safari stencils, cardboard inserts, tables | Meerkats select a stencil and create a Safari shirt. Fabric paint is the standard option. If using bleach-print shirts, adults handle all chemical steps outdoors behind a child-free boundary; children only choose stencils and observe.
12:50 | 45 min | Monkey’s Munchies Lunch | Food lead + assigned parents | Selected lunch ingredients, serving tables, mess kits, water | Serve one flexible camp lunch such as Lion Paw Sandwiches, Ranger Snack Boxes, or Herbivore Wraps. Reinforce handwashing and food-allergy controls.
13:35 | 20 min | Free Play & Water Break | All Burrow Leaders | Water station, shaded area, quiet activities | Keep the group within the campsite boundary. This allows families to reset after lunch before the next structured activity.
13:55 | 30 min | Elephant’s Trail: Animal Track Detectives | Nature lead + Burrow Leaders | Track cards, magnifiers, clipboards, crayons | Search for safe signs of animal life, insects, textures, and natural patterns. Meerkats share three interesting discoveries. Little Camper: Safari Walk.
14:30 | 20 min | Waterhole Snack Stop | Snack lead + parents | Selected fruit snack, water/juice, serving trays | Provide a seated shade break. Invite Meerkats to refill bottles and identify a healthy Safari Ranger choice.
14:50 | 35 min | Safari Wide Game: Waterhole Bingo | Games lead + Burrow Leaders | Safari bingo cards, crayons, picture markers | Hide picture cards around a clearly marked area. Work in Burrows, not as a race. Each child can help spot animals, tracks, leaves, or camp items.
15:30 | 45 min | Crafty Chameleon: Safari Lanterns or Animal Masks | Craft lead + adult helpers | Paper, card, glue, pre-cut pieces, LED tea lights only | Run a simple, pre-prepared craft. Adults handle cutting, hot glue, and any heat tools. Finished lanterns use LED tealights only.
16:20 | 35 min | Safari Walk & Nature Pause | Nature lead + all Burrow Leaders | Water, first aid, buddy markers | Take an easy, venue-approved walk. Stop to listen for savanna sounds, look for shapes in trees, and practise staying with a buddy. Eco-Warrior and Bug Hunter links can be recorded.
17:00 | 40 min | Bush Kitchen Preparation | Food lead + adult cooking team | Salad ingredients, safe child knives where approved, bowls, bread dough | Meerkats wash hands and complete simple supervised jobs: tear lettuce, add ingredients, stir, or portion bread dough. Little Camper: Bush Kitchen Prep. Cooking badge links apply where appropriate.
17:40 | 25 min | Campfire Circle | Campfire lead + fire safety adult | Fire area, seating boundary, songs, water/fire equipment | Explain the fire boundary before lighting. Lead Safari songs, a short story, and Burrow performances. Little Camper: Campfire Songs; Safety and Entertainer links.
18:05 | 60 min | Safari Braai / Supper | Food lead + parents | Selected dinner, mess kits, serving utensils, handwashing station | Adults control fires and cooking. Meerkats help with safe table jobs and their own bread or meal assembly under supervision. Include dietary alternatives and a separate Halaal set-up if required.
19:05 | 25 min | Safari S’mores or Trail Tracker Treats | Dessert lead + adult helpers | Selected treats, long handled tools if applicable | Use an adult-controlled fire area or a no-fire alternative. Keep portions simple and allergy-aware. Cooking: Sweet Treat opportunity.
19:30 | 35 min | Clean the Waterhole & Free Time | Clean-up lead + each Burrow | Basins, dish soap, sponges, drying towels, bins | Every family cleans mess kit items and helps restore their Burrow area. Little Camper: Clean the Waterhole / Tidy the Den.
20:10 | 30–40 min | Explorer’s Lookout: Night Walk & Stargazing (Optional) | Night activity lead + all Burrow Leaders | Adult torches, first aid, buddy markers, star guide | Only run if venue, weather, and adult numbers allow. Keep to a familiar route, use a buddy system, and finish early. Children do not need electronics. Little Camper: Stargazing.
21:00 | 15 min | Quiet Time & Bed Routine | Parents + Burrow Leaders | Toiletries, sleeping gear | Families prepare sleep spaces, brush teeth, make a final toilet visit, and settle calmly. Keep noise low around neighbouring campers.
21:30 | Overnight | Sleep Under the Stars | Parents + overnight Scouters | Sleeping gear, adult first-aid access | Each Meerkat sleeps in a tent or shelter with their parent/guardian. Little Camper: Sleep under the stars.
DAY 2 — Morning Safari Mission, Pack Down & Closing
07:30 | 30 min | Wake Up, Wash & Stretch | Burrow Leaders + parents | Water, toiletries, open area | Meerkats wash, dress, air sleeping bags/blankets, and take part in gentle animal-movement stretches. Little Camper: Tidy the Den.
08:00 | 40 min | Safari Breakfast | Breakfast lead + assigned parents | Selected breakfast ingredients, mess kits, water | Choose a flexible option such as Safari Flapjacks, Ranger Porridge, Campfire Toast, or Monkey Fruit Skewers. Adults supervise all heat and food preparation.
08:45 | 20 min | Meerkats Own & Reflection | Meerkats Own lead | Quiet spot, optional reflection cards | Create a calm moment to reflect on favourite Safari discoveries, camp rules, and how everyone helped their Burrow.
09:10 | 60 min | Lion’s Den Safari Games Circuit | Games lead + Burrow Leaders | Cones, soft balls, water relay equipment, rope | Offer age-appropriate stations such as Cheetah Run Relay, Zebra Tail Tag, Elephant Water Relay, and Crocodile Swamp Crossing. Use short turns, water breaks, and non-elimination rules.
10:10 | 20 min | Pack Down the Safari Base | All families + Burrow Leaders | Rubbish bags, site checklist | Families pack personal gear and clean their section. Meerkats take on safe jobs such as collecting small litter, rolling sleeping bags, and returning markers.
10:30 | 30 min | Closing Circle & Badge Celebration | Camp Leader + badge lead | Badge tracker, certificates/badges, camp song | Gather for the Meerkat Song, prayer/reflection, acknowledgement of helpers, and recognition of badge tasks completed. Explain any tasks to finish at a later Den meeting.
11:00 | — | Departure | Camp Leader + registration team | Sign-out list | Release Meerkats only to their parent/guardian. Confirm the camp area is checked, valuables collected, and the venue is handed back clean.